**PROCUREMENT PLAN**

(This is a republication of previous notices published on the following

Dates - Original: September 2021, Revision March 2023, Revision March 2024)

1. **GENERAL**

**Project Information**

Country: Belize

Grantee: Government of Belize

Project Name:  Enhancing the Belize National Quality Infrastructure

Implementing Agency: Belize Bureau of Standards

Bank’s Approval Date of the Procurement Plan: Original: August 2021;

Revision 1: March 2023;

Revision 2: March 2024.

Period Covered by This Procurement Plan: August 2021 – June 2024.

**II. GOODS AND WORKS AND NON-CONSULTING SERVICES**

1. **Prior Review Threshold:** Procurement decision subject to prior review by the Bank:

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Procurement Method** | **Prior Review Threshold** | **Comments** |
| 1. | Limited Bidding (LB) - National | ALL | Purchasing of mass standards. |
| 2. | Direct Selection (DS) | ALL | Calibration of mass standards. |

1. **Reference to (if any) Project Operational/Procurement Manual:** Procurement Policy for Projects Financed by CDB (November 2019), and Procurement Procedures for Projects Financed by CDB (January 2021).
2. **Any Other Special Procurement Arrangements:** For Goods and Services procured with funds from EPA and CSME Standby Facility eligibility for procurement shall be extended to countries eligible for procurement under EU-funded projects, which are not CDB Member Countries.
3. **Procurement Packages with Methods and Time Schedule**

| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Ref. No.** | **Contract Description** | **Estimated Cost**  **(EURO)** | **Procurement Method** | **Pre-**  **qualification (Yes/No)** | **Bank Review (Prior/Post)** | **Expected Bid-Opening/ Commencement Date** | **Comments** |
| **1** | Purchasing and delivery of E1 accuracy class mass standards  F2 accuracy class mass standards |  | Limited Bidding (National) | No | Prior | May 2023 | Contract signed with vendor on 13th February 2024 |
| **2** | Calibration of one (1) set of Mass standards (1 mg to 10 kg) |  | Direct Selection | No | Prior | April 2024 | Calibration at TTBS |
| **4** | Calibration of one (1) Pressure Transmitter, five (5) temperature probes, one (1) humidity probe |  | Direct Selection | No | Prior | April 2024 | Calibration at CENAM |
| **5** | Shipping and delivery of one (1) set of Mass standards (1 mg to 10 kg) |  | Direct Selection | No | Prior | April 2024 | Shipment through FedEx |

**III. CONSULTING SERVICES**

1. **Prior Review Threshold:** Procurement decision subject to prior review by the Bank:

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Selection Method** | **Prior Review Threshold** | **Comments** |
| 1. | Quality-Based Selection | All | For ISO 9001 Consultancy |
| 2. | Consultants Quality Selection | All | For ISO 17025 Consultancy. |

1. **Reference to (if any) Project Operational/Procurement manual**: Procurement Policy for Projects Financed by CDB (November 2019), and Procurement Procedures for Projects Financed by CDB (January 2021).
2. **Any Other Special Procurement Arrangements**: For Goods and Consulting Services procured with funds from EPA and CSME Standby Facility eligibility for procurement shall be extended to countries eligible for procurement under EU-funded projects, which are not CDB Member Countries.
3. **Indicative Procurement Packages with methods:**

| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Ref. No.** | **Description of Assignment** | **Estimated**  **Cost**  **(EURO)** | **Selection Method** | **Review by Bank** | **Expected Proposal Submission Date** | **Expected Start Date** | **Comments** |
| 1 | Consultancy Services-Design and deliver modules for trainer the trainers, stakeholders of BBS and BBS staff to audit and implement ISO 9001:2015 based on the quality management systems. |  | Quality- Based Selection | Prior | September 2022 | April 2023 | Contract signed with Firm on 27 March 2023 and Completed in October 2024 |
| 2 | Consultancy Services- Design and deliver a capacity development module for stakeholders of BBS and BBS staff to audit and implement ISO/IEC 17025:2017 based quality management systems. |  | Consultants Qualifications Selection | Prior | May 2023 | June 2024 | Evaluation in progress |

1. **IMPLEMENTATION AGENCY CAPACITY BUILDING WITH TIME SCHEDULE**

Project Launch Workshop: Completed

**To be determined in consultation with grant recipient.**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **No.** | **Expected Outcome/Activity Description** | **Estimated Duration** | **Start Date** | **Comments** |
| 1. | Project briefing meeting | 1 day | August 2021 | Completed |
| 2. | Project launch meeting | 1 day | October 2021 | Completed |
| 3. | Training on CDB e-learning modules | Self-pace | March 2023 | Completed |