PROCUREMENT PLAN

I.	General

- Project Information:

Country:	Belize

Borrower: 	The Government of Belize

Project Name:	Implementation of Multi-Hazard Impact-Based Forecasting and Early Warning System for the Belize River Watershed - Belize

Project Implementing Agency (PIA): Ministry of Economic Development, Belize

- Bank’s Approval Date of the Procurement Plan: December 2023

- Period Covered By This Procurement Plan: December 2023 – September 2026

II.	Goods and Works and Non-Consulting Services

- Prior Review Threshold: Procurement decision subject to Prior Review by the Bank as stated in the Procurement Procedures:

|  | Selection Method | Prior Review Threshold (USD) |
| --- | --- | --- |
| 1. | Limited Bidding - National: Goods/Non-consulting Services | ≥ 12,000 |
| 2. | Direct Selection | ≥ 12,000 |

- Reference to (if any) Project Operational/Procurement Manual: Procurement Policy for Projects Financed by CDB (November, 2019) and Procurement Procedures for Projects Financed by CDB (January, 2021).

- Any Other Special Procurement Arrangements: To comply with the requirements of the CARE Finance Agreement the following is required:

- Financing shall be provided under CARE and thus eligibility shall be extended to countries which are eligible for procurement under EU-Funded projects, which are not CDB member countries, in accordance with the EU Eligibility Rules.

- Procurement Packages with Methods and Time Schedule

| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref No. | Contract (Description) | Selection Method | Pre- qualification (Yes/No) | Regional Preference (Yes/No) | Review by Bank (Prior/ Post) | Expected Bid-Opening Date | Comments |
| 1. | Current Observation Network, Modelling and Analysis Tools Improved |  |  |  |  |  |  |
| (a) | Weather station parts | Direct Selection | No | No | Prior | September 2024 |  |
| (b) | Desktop computers (4), workstations (2), laptops (4), rugged field laptops (2), rack servers (2), hard drive and memory sticks | Direct Selection | No | No | Prior | June 2024 |  |
| (c) | GNC – a station equipment | Limited Bidding – National | No | No | Prior |  |  |
| (d) | Tsunami equipment for coastal at- risk communities | Limited Bidding - National | No | No | Post |  |  |
| 2. | Risk analysis and vulnerability assessment completed, and multi-hazard maps developed |  |  |  |  |  |  |
| (b) | Local Travel (10) | Limited Bidding - National | No | No | Post |  |  |
| (c) | Workshop/training (4) | Limited Bidding - National | No | No | Post |  |  |
| (e) | Local travel (5) | Limited Bidding - National | No | No | Post |  |  |
| 3. | Reliable and Operational Forecasting and Warning System Established |  |  |  |  |  |  |
| (a) | Public Awareness Campaign for CAP | Limited Bidding - National | No | No | Prior |  |  |
| (c) | Local travel (4) | Limited Bidding - National | No | No | Post |  |  |
| (d) | Workshops/Training (4) | Limited Bidding - National | No | No | Post |  |  |
| (e) | Public Awareness Campaign | Limited Bidding - National | No | No | Prior |  |  |
| 4. | NMS and NEMO Staff Capacity Improved |  |  |  |  |  |  |
| (b) | Workshop/Training (6) | Limited Bidding - National | No | No | Post |  | There are 6 workshops to be held at different times. |
| (c) | Distance Learning | Limited Bidding | No | No | Prior |  |  |
| (d) | On-Campus Learning UWI | Direct Selection | No | Yes | Prior |  |  |
| (e) | On-Campus Learning CIMH | Direct Selection | No | Yes | Prior |  | As at (d). |

III.	Consulting Services

- Prior Review Threshold: Procurement decision subject to Prior Review by the Bank as stated in the Procurement Procedures:

|  | Selection Method | Prior Review Threshold (USD) |
| --- | --- | --- |
| 1. | Individual Consultant Selection (ICS) | ≥12,000 |
| 2. | Quality Cost Based Selection (QCBS) | ≥40,000 |
| 3. | Direct Selection (DS) | ≥12,000 |
|  | Consultants Qualifications Selection (CQS) | ≥40,000 |

- Reference to (if any) Project Operational/Procurement Manual: Procurement Policy for Projects Financed by CDB (2019) and [Procurement Procedures for Projects Financed by CDB (January 2021)]

- Any Other Special Procurement Arrangements: Financing shall be provided under the CARE agreement and thus, in accordance with that agreement, eligibility shall be extended to countries which are eligible for procurement under the EU-funded Programme, which are not CDB member countries, in accordance with the EU Eligibility Rules.

- Procurement Packages with Selection Methods and Time Schedule

| 1 | 2 | 3 | 4 | 5 | 6 |
| --- | --- | --- | --- | --- | --- |
| No. | Assignment (Description) | Selection Method | Review by Bank (Prior/Post) | Expected Proposal Submission Date | Comments |
| - 1. | Project Coordinator | ICS | Prior | March 2024 |  |
|  | Consultancy Services – Establish a high availability Kubernetes server cluster for the NMS. configuration and maintenance | QCBS | Prior | June 2024 |  |
|  | Consultancy services – Update and expand flood EWS and conduct training on FEWS operation, configuration and maintenance | QCBS | Prior | June 2024 |  |
| - 2. | Consultancy services – Conduct risk analysis and vulnerability assessment for the Belize river watershed | CQS | Prior | July 2024 |  |
| - 4. | Consultancy services – Development of a multi-hazard impact-based forecast and EWS for the NMS. | QCBS | Prior | August 2024 |  |
|  | Consultancy Services – Capacity Building and Training for the NMS and NEMO – Belize | DS | Prior | May 2024 |  |
|  | Procurement Consultant | ICS | Prior | March 2024 |  |

IV.	Implementing Agency Procurement Capacity Building Activities with Time Schedule

In this section the agreed Procurement Capacity Building Activities are listed with time schedule.

| No. | Expected Outcome/ Activity Description | Estimated Cost | Estimated Duration | Start Date | Comments |
| --- | --- | --- | --- | --- | --- |
| 1. | Project launch workshop (virtual or in-person) with CDB and Implementing Agency to increase the capacity of Implementing Agency to follow CDB’s procurement procedures | 0 | 2 | Q2 2024 |  |

| ICB NCB DS LB RB FA NBF | International Competitive Bidding National Competitive Bidding Direct Selection Limited Bidding Regional Bidding Force Account Non-Bank Financing | QBS QCBS FBS LCS CQS ICS | Quality Based Selection Quality and Cost-Based Selection Fixed Budget Selection Least Cost Selection Consultants Qualifications Selection Individual Consultant Selection |
| --- | --- | --- | --- |