DRAFT TERMS OF REFERENCE

CONSULTANCY SERVICES FOR DEVELOPMENT OF GENDER-RESPONSIVE KNOWLEDGE AND INFORMATION PRODUCTS (KIPS) ON REGIONAL SPS STANDARDS AND GUIDELINES

- BACKGROUND

  - According to the Caribbean Development Bank (CDB) and the Food and Agriculture Organisation (FAO) 2019 Report on 'The State of Agriculture in the Caribbean', CDB/FAO 2019, there are several factors hindering the trade of agricultural products within the Region. Among them are unjustified sanitary and phytosanitary (SPS) measures, primarily due to the absence of regionally harmonised SPS standards, guidelines and protocols. As a result, exporters face considerable uncertainty and high and sometimes prohibitive costs when trading agricultural products within the Region. The situation runs counter to the principles enshrined in the CARICOM Single Market and Economy (CSME).

  - The CARICOM Heads of Government have expressed their intention to increase regional food production and trade and, through the Council for Trade and Economic Development (COTED - Agriculture), have launched the Road Map for Food Security in support of the 25 by 2025 initiative – the reduction of food imports by 25% by 20251/.

  - The absence of standardised agricultural trade practices and harmonised SPS measures within CARICOM poses a myriad of challenges and risks to the regional agri-food system, agri-enterprises, consumers, and the environment. These challenges include uncertainty, market access difficulties, increased business costs, safety concerns, and hindrances to growth and to enhancing the regional agri-food system/value chain.

  - Considering these challenges, establishing and adhering to uniform standards within the CARICOM community is crucial. Standardisation can streamline trade processes, reduce compliance costs, enhance consumer confidence, and facilitate the smooth functioning of regional supply chains. Moreover, standardised practices can strengthen CARICOM's collective bargaining power, enabling the Region to negotiate more favourable trade agreements on the international stage. By addressing these issues, CARICOM can foster a secure, competitive, and sustainable regional agri-food system and trading environment.

  - In 2021, the CDB supported the Caribbean Agricultural Health and Food Safety Agency (CAHFSA) by financing a Technical Assistance Grant for developing guidelines2/ to facilitate intra- regional trade in selected plant and animal products (Phase 1). The guidelines were adopted during the 104th Special Meeting of the Council for Trade and Economic Development (COTED-Agriculture) held on July 8, 2022. COTED also reached a unanimous consensus on the necessity for further efforts, specifically requesting: (1) the development of regional standards based on the approved guidelines, and

(2) assistance to  CDB Borrowing Member Countries (BMCs) in auditing their national SPS systems.

1/  The CARICOM Ministerial Taskforce (MTF) on Food Production and Food Security reported that in 2022 Member States were collectively able to achieve 57% of the target set in keeping with realising ‘Vision 25 by 2025’. The MTF report highlighted production data for targeted commodities (ginger, turmeric, corn, soya bean, root crops, fruits, cocoa, poultry, meat, fish, table eggs, and dairy) as CARICOM moves towards lowering the regional import bill.

2/ Animal Products (Eggs, Sheep and Goat Meat, Dairy Products, Beef and Honey) and Plant Products (Banana and Plantain, Onions and Escallions, Crucifers (Broccoli, Cauliflower, Lettuce, Cabbage, Pak choi), Cucurbits (Cucumber, Watermelon, Pumpkin, Squash), Legumes (Peas and Beans), Spices (Ginger and Turmeric), Solanaceous crops (Tomatoes, Peppers, Eggplant), Taro (Dasheen) and Eddo, Yam, Cassava, White Potatoes, Sweet Potatoes, Pineapple and Corn.

In response, CDB will support the next phase of this crucial initiative, which involves developing regional SPS standards and initiating a pilot program to audit national systems. This aims to strengthen the SPS regime and build human capital (public and private sectors), particularly for those involved in intra-regional trade in agricultural commodities.

- OBJECTIVE

  - The objective of the consultancy is to develop gender-responsive, knowledge and information products (KIPS) on regional SPS Standards and Guidelines for training and capacity-building of stakeholders/value chain actors produced in BMCs. The KIP’s will be based on the recommendations emanating from Components 1 and 2 of this Project.

- SCOPE OF SERVICE

  - To achieve the stated objective, the consultancy will focus on developing high-quality, visually engaging, scientifically sound, and practice-based state-of-the-art content on a range of SPS issues within the relevant segments of the agri-food chain. The KPIs will be presented as traditional communication products, such as fact sheets and brochures, as well as multimedia aids—short videos, photographs, and infographics—that are suitable for and accessible on smart devices (e.g., smartphones) and other communication platforms. The products will be created using a standardised format to ensure consistency and uniformity, with all relevant gender issues considered. Specifically, the consultancy will:

    - Produce ten (10) high-quality instructional videos between 3 – 10 minutes and ten (10) short clips between 1 – 3 minutes on SPS-related issues and other relevant topics of importance for trade in agricultural commodities.

    - Produce twenty (40) action photos featuring actors and service providers engaged in appropriate practices in selected value chains in BMCs.

    - Produce ten (10) infographics depicting appropriate SPS systems related to the export of agricultural commodities.

    - Produce ten (10) fact sheets on specific SPS-related topics.

  - The Consultant(s) shall be responsible for:

    - Development of the overall concepts and scenarios for KIPs and agreement on content.

    - Development of script and storyboards.

    - Submission of the script and storyboards for review and validation by CAHFSA, CRFM, and the TAC.

    - Filming and documenting practices/activities.

    - Interviewing relevant stakeholders (value chain actors, technical specialists, policy makers, consumers, etc.) to collect sound bites and other relevant information.

    - Collecting and collating information required (video footage, pictures, and audio) for preparation of KIPs for the following focus areas:

      - Plant quarantine systems.

      - Border control and protection.

      - Livestock and fisheries production.

      - Pesticide application and management.

      - Official control systems for food safety.

    - Production of all KIPs according to the agreed formats and specifications - 10 videos (two on each focus area), 10 short clips (two on each focus area), 40 action photos (eight on each focus area), 10 infographics (two on each focus area) and 10 fact sheets (two on each focus area).

    - Presentation of KIPs for review/validation by CAHFSA, CRFM and TAC.

    - Editing audio balancing, sub-titling, and finalising following comments from CAHFSA, CRFM and TAC.

    - Preparation of protocols for accessing, uploading and storing KIPs.

  - The Consultant will be required to undertake all the activities necessary to accomplish the stated objective of the Project. This will be carried out under the overall direction and supervision of CAHFSA, CRFM, and TAC. This includes but is not limited to the following:

    - Review all relevant and available information at the national/regional level for preparation of KIPs.

    - Review global best practices for preparation of KIPs, including the Principles for Digital Development3.

    - Review relevant intellectual property agreements (CDB, CAHFSA, CFRM and other relevant entities).

    - Review regulations with regard to branding and crediting (CDB, CAHFSA, CFRM and other relevant entities).

- DELIVERABLES AND REPORTING REQUIREMENTS

  - The Consultant will be required to submit/deliver the following:

| Reports/Deliverables | Timeframe |
| --- | --- |
| Inception Report - Work plan including the methodology and the approach to be adopted - overall concepts and scenarios for KIPs, and a format for script and storyboards. Detailed timeline for project activities. | The report should be submitted within 1 month of the commencement of the assignment. |
| Progress Report - Update on assignment, including the activities commenced, progress to date and any challenges with implementation. The report should also include proposed solutions to challenges articulated and related timeframes. | This will be submitted 3 months after the assignment commences. |
| Outputs 1: Submission of 5 draft videos, 5 draft short clips, 10 action photos, 5 infographics and 5 fact sheets. | This will be submitted 6 months after the assignment commences. |

3	Nine living guidelines that are designed to help integrate best practices into technology-enabled programs and are intended to be updated and refined over time.

| Reports/Deliverables | Timeframe |
| --- | --- |
| Output 2: Submission of draft KIPs, including 10 draft videos, 10 short clips, 40 action photos, 10 infographics and 10 fact sheets. | This will be submitted 9 months after the assignment commences. |
| Outputs 3: Submission of completed KIPs - 10 videos, 10 short clips, 40 action photos, 10 infographics and 10 fact sheets. | This will be submitted 11 months after the assignment commences. |
| Final Report - Report listing outputs, containing lessons learned and recommendations for follow-up actions for future development of KIPs. | This will be submitted 12 months after the assignment commences. |

  - All reports and supporting documents should be produced in Microsoft Word and submitted electronically to CAHFSA.

- IMPLEMENTATION ARRANGEMENTS

  - The Consultant will work under the guidance of the Project Coordinator -CAHFSA.

- DURATION, QUALIFICATIONS AND EXPERIENCE

  - The assignment will be executed over 12 months. The Consultancy Firm should have:

    - No less than five years’ overall consulting experience, with specific experience in the use of digital tools and the development of media content for smart devices and other platforms.

    - Excellent technical capacities (state-of-the-art filming equipment, preferably High Definition) to ensure smooth and high-quality production.

    - Successfully completed at least two similar assignments.

    - Key experts as outlined at 6.05.

  - Team members should possess a Bachelor’s degree in ICT or a related field, such as video and film production, photography, or cinematography, along with a minimum of 3 years of relevant professional experience. Alternatively, they may hold a relevant professional qualification, complemented by at least 5 additional years of experience or equivalent expertise. The Team Leader should have at least 5 years of experience managing teams on similar projects. Additionally, team members should have knowledge and experience in the agricultural sector within the Caribbean or Small Island Developing States and be aware of gender issues in the sector and considerations for developing KIPs...

  - More specific details as it relates to qualifications and experience are as follows:

    - Demonstrated experience in conception, production and editing of short videos.

    - Proven experience in videography/video editing.

    - Experience covering social and development subjects will be an asset.

    - Knowledge of ethical standards in reporting/documenting issues related to marginalised groups will be an asset.

    - Extensive experience in producing digital media content for regional or international organisations with the aim of reaching local audiences will be an asset.

    - Proven experience in disseminating digital media information/communication products.

  - Other technical competencies include:

    - Proficiency in report writing.

    - Excellent analytical skills.

    - Excellent oral and written skills.

  - Key Experts Required:

    - Videographer (Team Leader).

    - Video Editor.

    - Script Writer and Editor.

    - Photographer.