PROCUREMENT PLAN

All Estimated Costs are in USD

- General

- Project Information:

Country: Trinidad and Tobago

Beneficiary: Government of Trinidad and Tobago

Project Name: Building National and Community Capacity for Climate and Disaster risk-informed Decision Making

Project Implementing Agency: Office of Disaster Preparedness and Management, Ministry of Homeland Security

- Bank’s Approval Date of the ProcureRisk-Informedment Plan:	 Original: May 15, 2026

- Period Covered by this Procurement Plan: July 01, 2026 to April 2027

- Goods and Non-Consulting Services

- Prior Review Threshold: Procurement decision subject to Prior Review by the Bank.

| Selection Method | Prior Review Threshold | Comments |
| --- | --- | --- |
| NCB | >50,000 |  |
| LB | >20,000 |  |
| DS | >10,000 |  |

- Prequalification: Not applicable.

- Reference to (if any) Project Operational/Procurement Manual: Procurement Policy for Projects Financed by CDB (2019) and the Procurement Procedures for Projects Financed by CDB (January, 2021)]

- Any Other Special Procurement Arrangements: n/a

- Procurement Waivers: Not applicable.

- Procurement Packages with Selection Methods and Time Schedule

| Ref No. | Contract (Description) | Selection Method | Prequalification (Yes/No) | Regional Preference (Yes/No) | Review by Bank (Prior/ Post) | Expected Bid-Opening Date | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.0 | Stakeholder Workshops | DS | No | No | Prior (if a single contract exceeds USD10,00) | January 2027 | Existing contracts have been awarded to firms previously selected through the National Competitive Bidding (NCB) method in accordance with the applicable local OPR regulations. These firms have satisfactorily completed similar works within the past 12 months, with contract prices determined to be consistent with prevailing market rates. |
| 1.1 | Project Launch Workshop |  |  |  |  |  |  |
| 1.1.1 | Catering |  |  |  |  |  |  |
| 1.1.2 | Event Rental |  |  |  |  |  |  |
| 1.1.3 | Airfare and Accommodation for Tobago Participants |  |  |  |  |  |  |
| 1.1.4 | AV Equipment, Transportation and Facilitation | NBF | N/A | N/A | N/A |  |  |
| 1.2 | Preliminary Assessment Workshop | DS | No | No | Prior (if a single contract exceeds USD10,00) |  |  |
| 1.2.1 | Catering |  |  |  |  |  |  |
| 1.2.2 | Event Rental |  |  |  |  |  |  |
| 1.2.3 | Airfare and Accommodation for Tobago Participants |  |  |  |  |  |  |
| 1.2.4 | AV Equipment, Transportation and Facilitation | NBF | N/A | N/A | N/A |  |  |
| 1.3 | Sector and Community Data Collection and Training Workshops | DS | No | No | Prior (if a single contract exceeds USD10,00) |  |  |
| 1.3.1 | Catering |  |  |  |  |  |  |
| 1.3.2 | Event Rental |  |  |  |  |  |  |
| 1.3.4 | AV Equipment, Transportation and Facilitation | NBF | N/A | No | N/A | January 2027 |  |
| 2.0 | Communication activities |  | N/A | No | Prior | April 2027 |  |
| 2.1 | Development of Communication Products | NCB | No |  |  |  |  |
| 2.2 | Publication of Communication Products | NCB | N |  |  |  |  |
| 3.0 | Procurement of Equipment and Software |  |  | No | Post (if value is below 21,000 USD) | December 2026 | Due to the low value and risk, LB using pre-qualified suppliers via the local OPR system will provide adequate competition while ensuring an efficient, economical, and timely procurement process. These firms have demonstrated the necessary expertise and experience with prices determined to be consistent with prevailing market rates. |
| 3.1 | Procurement of Tablets | LB (National) | No |  |  |  |  |
| 3.2 | Purchase of Modelling Software (Two-Year License) | LB | No |  |  |  | Few firms available that are qualified and authorized distributors of the required products and having demonstrated the necessary experience and expertise to perform the required scope of work. |
| 3.3 | Purchase of ARC Geographic Information System License (Two-Year License) | LB | No |  |  |  |  |
| 3.4 | Building of Web-based Portal | LB | No |  |  |  |  |

- Consulting Services

- Prior Review Threshold: Procurement decision subject to Prior Review by the Bank as stated in the Procurement Procedures.

| Selection Method | Prior Review Threshold | Comments |
| --- | --- | --- |
| QCBS | ALL |  |
| ICS | ALL |  |

- Reference to (if any) Project Operational/Procurement Manual: Procurement Policy for Projects Financed by CDB (2019) and the Procurement Procedures for Projects Financed by CDB (January, 2021)

- Any Other Special Procurement Arrangements: n/a

- Procurement Packages with Selection Methods and Time Schedule

| 1 | 2 | 4 | 5 | 6 | 7 |
| --- | --- | --- | --- | --- | --- |
| Ref No. | Assignment (Description) | Selection Method | Review by Bank (Prior/Post) | Expected Proposal Submission Date | Comments |
|  | Consultancy Services for Building National and Community Capacity for Climate and Disaster Risk-Informed Decision Making | QCBS | Prior | December 2026 |  |
|  | Procurement Specialist | ICS | Prior | August 2026 |  |

IV.	Implementing Agency Procurement Capacity Building Activities with Time Schedule

| No. | Expected Outcome/ Activity Description | Estimated Cost | Estimated Duration | Start Date | Comments |
| --- | --- | --- | --- | --- | --- |
| 1. | Project launch workshop (virtual) with CDB and Implementing Agency to increase the capacity of Implementing Agency to follow CDB’s procurement procedures | 0 | 1 day | Q4 2026 |  |
| 2 | Increased capacity of Implementing Agency to undertake procurement in accordance with CDB’s Procurement Procedures through CDB’s Online Procurement Training. | 0 | 20 hours | Q4 2026 | 8 persons from ODPM passed CDB’s eLearning Courses 1, 2 and 3. All three courses can be completed in 20 contact hours and are self-paced. |

| ICB NCB DS LB RB FA NBF | International Competitive Bidding National Competitive Bidding Direct Selection Limited Bidding Regional Bidding Force Account Non-Bank Financing | QBS QCBS FBS LCS CQS ICS | Quality Based Selection Quality and Cost-Based Selection Fixed Budget Selection Least Cost Selection Consultants Qualifications Selection Individual Consultant Selection |
| --- | --- | --- | --- |