PROCUREMENT PLAN

All Estimated Costs are in USD

- GENERAL

- Project Information

| Country: | Saint Lucia |
| --- | --- |
| Recipient: | The Government of Saint Lucia |
| Project Name: | Upgrade of the Hydrometeorological Network and Support for Integrated Water Resources Management in Saint Lucia |
| Implementing Agency: | Water Resources Management Agency |

- Bank’s Approval Date of the Procurement Plan:  October 1, 2025

- Period covered by this Procurement Plan: October 1, 2025 – September 30, 2026

II.	GOODS AND WORKS AND NON-CONSULTING SERVICES

- Prior Review Threshold: Procurement decision subject to prior review by the Bank as stated in Procurement Procedures.

| Procurement Method | Prior Review Threshold, USD | Comments |
| --- | --- | --- |
| ICS | ≥5,000 |  |
| LB | ≥9,000 |  |
| DS | All contracts |  |

- Reference to relevant Procurement Framework: Procurement Policy for Projects Financed by CDB (November 2019) and Procurement Procedures for Projects Financed by CDB (January 2021)

- Any Other Special Procurement Arrangements: None

- Procurement Waivers: None

- Procurement Packages with Methods and Time Schedule for Goods and Non-Consulting Services

| 1 | 2 | 4 | 5 | 6 | 7 | 8 | 9 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref No. | Contract – Description | Selection Method | Prequalification (Yes/No) | Regional Preference (Yes/No | Review by Bank (Prior/Post) | Expected Bid Opening Date | Comments |
|  | Equipment upgrades and installation at monitoring stations | LB | Yes | No | Prior | October 2026 |  |
|  | Installation of anti-theft security measures for monitoring stations | LB | Yes | No | Prior | December 2026 |  |
|  | Acquisition of GIS software | DS | No | No | Post | July 2026 | In an effort to standardise the current GIS tools that the WRMA uses which is ArcGIS supplied by the regional supplier of ESRI solutions which is Spatial Innovision Limited based in Jamaica, the purchase of 2 annual, organisational licenses for a 2-year period will be done directly through the Caribbean ESRI supplier, Spatial Innovision Limited. |
|  | Acquisition of modelling PCs | LB | No | No | Post | July 2026 | These PCs will be sourced from suppliers pre-registered with the GOSL. |

Page 2

III.	CONSULTING SERVICES

- Prior Review Threshold: Procurement decision subject to Prior Review by the Bank as stated in the Procurement Procedures:

|  | Selection Method | Prior Review Threshold | Comments |
| --- | --- | --- | --- |
| 1. | Firms: QCBS | All Contracts |  |
| 2. | Individual Consultant Selection | All Contracts |  |

- Reference to (if any) Project Operational/Procurement Manual:  Procurement Policy for Projects Financed by CDB (2019) the Procurement Procedures for Projects Financed by CDB (January, 2021)

- Any Other Special Procurement Arrangements: None

- Procurement Packages with Selection Methods and Time Schedule for Consulting Services

| Ref No. | Assignment (Description) | Selection Method | Review Bank (Prior/Post) | Expected Proposal Submission Date | Comment |
| --- | --- | --- | --- | --- | --- |
|  | Upgrade of the Hydrometeorological Network and Support to Implement IWRM | QCBS | Prior | April 2026 |  |
|  | Project Coordinator | ICS | Prior | December 2025 |  |
|  | Procurement Specialist | ICS | Prior | January 2026 |  |
|  | Communications and Stakeholder Engagement Specialist | ICS | Prior | February 2026 |  |

- Implementing Agency Procurement Capacity Building Activities with Time Schedule

| No. | Expected Outcome/ Activity Description | Estimated Cost, USD | Estimated Duration (days) | Start Date | Comments |
| --- | --- | --- | --- | --- | --- |
| 1. | Virtual project kick-off meeting inclusive of CDB and Implementing Agency to increase the capacity of Implementing Agency to follow CDB’s procurement procedures | Not applicable | 1 | Q1 2026 |  |
| 2 | Increased capacity of Executing Agency to undertake procurement in accordance with CDB’s Procurement Procedures through CDB’s Online Procurement Training. | Not applicable | 5 | Q1 2026 | Persons from the WRMA are enrolled. All three courses can be completed in twenty (20) contact hours and are self-paced. |

Page 4