REVISED PROCUREMENT PLAN

All Estimated Costs Are In USD

- General

  - Project Information

Country: 	Grenada

Borrower: 	Government of Grenada

Project Name: 	Grenada Education Enhancement Project - Phase II

Implementing Agency:	Ministry of Education

  - Bank's Approval Date of the Procurement Plan: December 31, 2020 (Original) (Revised: November 2025, Revision 2: June 2026)

  - This Procurement Plan is valid until: December 31, 2026

  - Prior Review Threshold: Procurement decision subject to prior review by the Bank as stated in Appendix 2 of the Guidelines for Procurement:

| Procurement Method | Prior Review Threshold (USD) | Comments |
| --- | --- | --- |
| ICB Works | Greater than or equal to 1,000,000 |  |
| NCB - Works | Greater than or equal to 100,000 |  |
| ICB - Goods | Greater than or equal 100,000 |  |
| LB National | Greater than or equal to 90,000 |  |
| QCBS | Greater than or equal 500,000 |  |
| ICS | Greater than 50,000 |  |
| NBF | Not applicable | Procurement procedures of GOGR apply. |
| DS | Greater than 30,000 |  |

  - Reference to relevant Procurement Guidelines:  Procurement Policy for Projects Financed by CDB (November 2019) and updated to the Procurement Procedures for Projects Financed by CDB (January 2021)

  - Any Other Special Procurement Arrangements: For contracts financed using Agence Française De Développement (AFD) resources, procurement eligibility shall be extended beyond CDB member countries to include French individuals and entities in accordance with the CDB-AFD Credit Facility Agreement. For contracts using these resources, AFD procurement requirements, including publication on relevant platforms indicated in the AFD Agreement, will be observed.

  - Procurement Waivers: No procurement waivers are required for this project.

PROCUREMENT PLAN

Goods Works and Non-Consulting Services

Page 2

| Ref No. | Contract (Description) | Procurement/ Selection Method | Prequalification (Yes/No) | Review by Bank (Prior/Post) | Expected Bid- Opening Date | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 73610-G-6a | Furniture for classrooms: St Andrews Anglican Primary School | ICB | No | Prior | September 2027 |  |
| 73610-G-6c | Furniture for classroom: Grenada Christian Academy | ICB | No | Prior | July 2026 |  |
| 73610-G-6 (b,d) | Furniture for staff and laboratory - Grenada Christian Academy and the St Andrews Anglican Primary School | ICB | No | Prior | July 2026 |  |
| 73610-G-6 (e,i) | Furniture for staff: St Joseph’s Convent, St Andrew’s & J.W. Fletcher Memorial Secondary School | NCB | No | Post | September 2027 |  |
| 73610-G-6f | Furniture for classroom: St Joseph’s Convent, St Andrew’s | NCB | No | Post | September 2027 |  |
| 73610-G-6g | Furniture for classroom: J.W. Fletcher Memorial Secondary School | NCB | No | Post | September 2027 |  |
| 73610-G-6ai | Furniture: St. David’s Roman Catholic School | ICB | No | Prior | September 2027 |  |
| 73610-G-7a | Equipment: Grenada Christian Academy | ICB | No | Prior | September 2026 |  |
| 73610-G-7c | Equipment: St. David’s Roman Catholic School | ICB | No | Prior | September 2027 |  |
| 73610-G- IS- 2a | Furniture and equipment: Sensory rooms and corners | ICB | No | Prior | July 2026 | The items for sensory corners and room are the same with sensory corners having additional items both for sensory items, IT and school supplies. All the items will be delivered to the Ministry of Education for distribution to the schools. Economies of scale will be achieved through bulking of the procurement activities. The other activities are NCB and LB based on the cost of the activity. |
| 73610-G- IS- 2b | IT equipment: sensory corners | NCB | No | Post | July 2026 |  |
| 73610-G- IS- 2c | School Supplies for sensory corners | LB National | No | Post | July 2026 |  |
| 73610-G-IS - 1 | Portable ramps | NCB | No | Post | July 2026 |  |
| 73610-G-IS- 3a | Home Economics Equipment: Victoria Special Needs Institution | NCB | No | Post | July 2026 | Activity has been split based on the type of items. Given the split and the new distribution, the activities fall under the threshold for ICB and so the new procurement method is NCB. The new fees are also under the review threshold. |
| 73610-G-IS- 3b | General Items: Victoria Special Needs Institution | NCB | No | Post | July 2026 |  |
| 73610-G-IS- 3c | IT equipment: Victoria Special Needs Institution | NCB | No | Post | July 2026 |  |
| 73610-G-IS-5 a | Indoor and Outdoor Play and Learning Equipment and Resources for 20 public pre-primary centres | ICB | No | Prior | July 2026 | The activities are being divided based on the type of goods to be procured as the items for the schools are of the same technical specifications, with slight difference in items and quantities. Only the fire extinguishers selection methods and review have changed; it is Limited bidding given the market is limited and it also falls below the prior review threshold. |
| 73610-G-IS-5 b | Information Technology Equipment for 20 public pre-primary centres | ICB | No | Prior | July 2026 |  |
| 73610-G-IS-5 c | Safety items / Fire Extinguishers for 20 public pre-primary centres | LB National | No | Post | July 2026 |  |
| 73610-G-IS-5 d | Furniture for 20 public pre-primary centres | NCB | No | Post | July 2026 | Government’s policy decision is that student’s furniture to be made locally for maintenance and repairs |
| 73610-G-IS-4 | Procurement of universal screening, progress monitoring and clinical assessment tools | DS | No | Prior | July 2026 |  |
| 73610-W-1 | Grenada Christian Academy Works | ICB | No | Prior | May 2022 | Contract awarded |
| 73610-W-2 | St. Andrews Anglican Primary Works | ICB | No | Prior | January 2024 | Contract awarded |
| 73610-W-3 | J.W. Fletcher Catholic Secondary Works | ICB | No | Prior | July 2026 |  |
| 73610-W-4 | St. Joseph's Convent - St. Andrews Works | ICB | No | Prior | July 2026 |  |
| 73610-W-5 | St David’s Roman Catholic Secondary School Works | ICB | No | Prior | May 2024 | Contract awarded |
| 73610-NCS-1 | Digitization of Standard Operating Procedures | CQS | No | Prior | October 2026 |  |
| 73610-CB-IS - 2 | Postgraduate Degree in Speech and Language Pathology for Two Persons | LB | No | Prior | September 2026 |  |  |
| 73610-CB-IS - 3 | Postgraduate Degree in Occupational Therapy for Two Persons | LB | No | Prior | September 2026 |  |  |
| 73610-CB-IS - 4 | Postgraduate Degree in Physical Therapy for Two Persons | LB | No | Prior | September 2026 |  |  |
| 73610-CB-IS - 5 | Short Course: Cognitive Behavioral Therapy for Guidance Counselors, SEN, and ECD officers | LB | No | Prior | July 2026 | MOU signed June 8, 2026, actual cost USD 19,125.00 |  |
| 73610-CB-IS - 6 | Short Course: Personal Protection and Defense for Guidance Counselors (36), SEN Officers (7), and 2 teachers per secondary school (42) (split over two years) | LB | No | Prior | October 2026 |  | Page 3 |
| 73610-CB-IS - 7 | Certification Training in Early Childhood Care and Development for 30 ECD practitioners | DS | No | Prior | February 2026 | 1-year training with UWI Global campus is ongoing. |  |
| 73610-CB-IS - 8 | Certification in Hi-Scope for 8 ECD officers | DS | No | Prior | February 2026 | This activity will be financed using local Ministry of Education (MOE) funds, as the country of origin is not an eligible CDB member country. Consequently, the expenditure is not eligible for financing under the CDB-funded project. An alternative course or area of study that qualifies for CDB support should therefore be identified and indicated for consideration. |  |
| 73610-CB-IS - 9 | Certification in Planning for quality and equitable early childhood education – UNESCO IIEP | DS | No | Prior | October 2026 |  |  |
| 73610-NC-IS - 1 | Digitization of SOPs and information requests across Departments | NCB | No | Post | Q1 2027 |  |  |
| 73610-CB-IS - 10 | Workshop Costs: Open EMIS and Learning Management System (2-day training annually, 100 for 2025 and 150 for years 2025-2028) | LB | No | Prior | Q1 2027 |  |  |
| 73610-CB-IS - 11 | IIEP Course: Using Learning Assessment Data to Monitor SDG 4 Progress for 4 persons | DS | No | Post | October 2026 |  |  |
| 73610-CB-IS - 12 | 3-day sensitization and planning meeting for EIS | LB | No | Post | Q1 2027 | Grenada selected via the collaboration with the CDB and IDB under the Regional Public Good |  |
| 73610-CB-IS - 13 | Two Day workshop with ECD and Sen MOE staff on enhancing screening tools | LB | No | Post | November 2026 |  |  |
| 73610-CB-IS - 14 | Workshop for 360 appraisals | LB | No | Post | Q1 2027 |  |  |
| 73610-CB-IS - 20 | Stakeholder workshops for EIS policy and legislation updates and implementation | LB | No | Post | October 2026 |  |  |
| 73610-CB-IS - 15 | Workshop for guidance counselors in universal screening, progress monitoring and clinical assessment tools | LB | No | Post | Q1 2027 |  |  |
| 73610-CB-IS - 16 | 3-Day leadership retreat for MOE heads of Department to facilitate development of SOPS | LB | No | Post | Q1 2027 |  |  |
| 73610-CB-IS - 17 | Workshop for Open IIEP and Learning Management for 180 IEPs (all primary and secondary) System | LB | No | Post | Q1 2027 |  |  |
| 73610-CB-IS - 18 | Workshops retreat for student council and leadership program | LB | No | Post | October 2026 |  |  |
| 73610-CB-IS - 19 | Workshop for Consultancy to develop the cost operational guidelines for the ECD Council and support start up activities for the council | LB | No | Post | October 2026 |  | Page 4 |

Consulting Services

- Prior Review Threshold: Procurement decision subject to Prior Review by the Bank as stated in the Procurement Procedures: [Thresholds for applicable procurement selection methods (not limited to the list below) will be determined by CDB based on a risk assessment of the project, implementing agency, and the market]

|  | Selection Method | Prior Review Threshold | Comments |
| --- | --- | --- | --- |
| 1. | Firms: QCBS | All Contracts |  |
| 2. | Firms: Direct Selection | All Contracts |  |
| 3. | Individual Consultant Selection | All Contracts |  |
| 4. | CQS | All Contracts |  |

- Reference to (if any) Project Operational/Procurement Manual: Procurement Policy for Projects Financed by CDB (2019) and the Procurement Procedures for Projects Financed by CDB (January 2021)

- Any Other Special Procurement Arrangements: For contracts financed using Agence Française De Développement (AFD) resources, procurement eligibility shall be extended beyond CDB member countries to include French individuals and entities, in accordance with the CDB-AFD Credit Facility Agreement. For contracts using these resources, AFD procurement requirements, including publication on relevant platforms indicated in the AFD Agreement, will be observed.

Consulting Services

Page 6

| Ref No. | Assignment (Description) | Selection Method | Review by Bank (Prior/Post) | Expected Proposal Submission Date | Comments |
| --- | --- | --- | --- | --- | --- |
| 73610-C-5 a | Construction Supervision Engineering Services for Grenada Christian Academy | DS | Prior | December 2023 | Contract awarded |
| 73610-C-5 b | Design Review and Construction Supervision Engineering Services for St. Andrews Anglican Primary | QCBS | Prior | June 2025 September 2024 | Contract awarded |
| 73610-C-5 c | Design Review and Construction Supervision Engineering Services for J.W. Fletcher Catholic Secondary School) | QCBS | Prior | December 2024 | Contract awarded |
| 73610-C-5 d | Design Review and Construction Supervision Engineering Services St Joseph’s Convent St Andrews | NBF | Post | November 2025 | Ongoing |
| 73610-C-5 e | Construction Supervision Engineering Services St David’s Roman Catholic Secondary School | NBF | Post | September 2025 | Ongoing |
| 73610-C-7 | Consultancy- capacity building for ECD-Secondary Teachers and Guidance counsellors on gender(ed) norms, practices, and gender responsive pedagogies | ICS | Prior | May 2026 | Advertised |
| 73610-C-8 | Consultancy-Early Identification System Implementation Support | ICS | Prior | March 2026 | Grenada was selected by the collaboration with the CDB and IDB under the Regional Public Good initiative to design a context-specific EIS. UWI was the selected Institution. |
| 73610-C-9 | Consultancy Services to Augment the Grenada Reading Screening Tool and Early Childhood Development Checklist | ICS | Prior | May 2026 | Advertised |
| 73610-C-10 | Consultancy Services to Update the Grenada Education Act, Develop Supporting Legislation And Policies, Memoranda Of Understanding, And Operational Manuals To Support Implementation of the Early Identification System (EIS) | QCBS | Prior | June 2026 |  |
| 73610-C-11 | Consultancy Services to Develop and Manage the Implementation of a Public Awareness Campaign Strategy for the Early Identification System (EIS) and Early Childhood Development (ECD) Standards | QCBS | Prior | May 2026 | Advertised |
| 73610-C-12 | Consultancy Services to Develop Costed Operational Guidelines for the Early Childhood Development (ECD) Council and Support Start-Up Activities | ICS | Prior | May 2026 | TOR and EOI sent to the bank. NOB approval received |
| 73610-C-13 | Consultancy to Develop a Costed Parental Engagement Plan and Provide Advisory Support for the First Year of Implementation | ICS | Prior | October 2026 |  |
| 73610-C-14 | Consultancy to Facilitate the Development of Standard Operating Procedures, Terms of Reference, and Communication Flow for School Support and Supervision Teams: Curriculum Officers, Education Officers, and Student Support Services | ICS | Prior | October 2026 |  |
| 73610-C-15 | Consultancy Services to Develop a Policy and Standard Operating Procedures for 360 Appraisals in Schools and Strengthen School Continuous Improvement Planning | CQS | Prior | October 2026 |  |
| 73610-C-16 | Consultancy to evaluate 360 appraisal system and CSSI implementation | CQS | Prior | May 2028 |  |
| 73610-C p 17 | Consultancy to Develop and Implement a Gender-Responsive Leadership Program for Student Leaders Identified Across Schools and Strengthen Student Councils | ICS | Prior | October 2026 |  |
| 73610-C- 18 | Consultancy Services for Institutional Strengthening Support Coordinator (ISSC) | ICS | Prior | June 2025 | Contract signed in October 2025 |

Page 7

- Procurement Capacity Building activities for the Implementing/Executing Agency

Project Launch Workshop for CDB financed component: Completed in February 2024 and will be completed by February 2025 for GPE financed component

The provision of online procurement e-learning by the CDB (21 days): to be completed between February- May 2025 (completed)

| Goods, Works, and Non-Consultancy Services | Consultancy Services: |
| --- | --- |
| NCB - National Competitive Bidding ICB - International Competitive Bidding RCB - Regional Competitive Bidding LB - Limited Bidding DS - Direct Selection FA - Force Account CP - Commercial Practices APA - Alternative Procurement Arrangements NBF - Non-Bank Financed | QCBS - Quality and Cost-Based Selection QBS - Quality-Based Selection FBS - Fixed Budget Selection LCS - Least-Cost Selection CQS - Consultants' Qualification Selection DS - Direct Selection CP - Commercial Practices APA - Alternative Procurement Arrangements ICS - Individual Consultants Selection NBF - Non-Bank Financed |