REVISED PROCUREMENT PLAN

All Estimated Costs Are In USD

- General

All Estimated Costs Are In USD

- General

- Project Information

Country: 	St. Vincent and the Grenadines

Borrower: 	Government of St. Vincent and the Grenadines

Project Name: 	School Improvement Project I

Implementing Agency: 	Ministry of Finance, Economic Planning, Sustainable Development and Information Technology

- Bank's Approval Date of the Procurement Plan:  Original: December 10, 2020

Revision 1: October, 2023

- This Procurement Plan is valid until: 	December 31, 2026

- Prior Review Thresholds: Procurement decision subject to prior review by the Bank.

| Procurement Method | Prior Review Threshold | Comments |
| --- | --- | --- |
| ICB Works | Greater than or equal to 1,000,000 |  |
| NCB - Works | Greater than or equal to 100,000 |  |
| ICB - Goods | Greater than or equal 100,000 |  |
| LB- Goods | Greater than 10,000 | National bidding. |
| ICS – Consulting Services | Greater than 10,000 |  |
| QCBS – Consulting Services | Greater than 150,000 |  |
| DS – Consulting Services | All |  |
| NBF | Not applicable | Procurement procedures of GOSVG apply. |

- Goods Works and Non-Consulting Services

| Ref No. | Contract (Description) | Procurement/ Selection Method | Prequalification (Yes/No) | Review by Bank (Prior/Post) | Expected Bid- Opening Date | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 73595-W-1 | Refurbishment of the Barrouallie Government Primary School | NCB | No | Prior | April 2021 | Procurement completed |
| 73595-W-2 | Refurbishment of the Barrouallie Anglican Primary School | NCB | No | Prior | April 2021 | Procurement completed |
| 73595-W-3 | Refurbishment and expansion of the Kingstown Anglican School | ICB | No | Prior | December 2023 | Procurement completed |
| 73595-W-4 | Refurbishment of the Charles Adam Anglican High (Bequia Community High School) | ICB | No | Prior | April 2021 | Procurement completed |
| 73595-W-5 | Refurbishment of the Main Block, St. Vincent Grammar School | NCB | No | Prior | January 2021 | Procurement completed |
|  | St. Vincent Grammar School | NCB | No | Prior | January 2021 | Procurement completed |

APPENDIX I

Page 2

| 73595-W-6 | Refurbishment of St. Vincent Girls High School Phase 1 | ICB | No | Prior | April 2021 | Procurement completed |
| --- | --- | --- | --- | --- | --- | --- |
|  | St. Vincent Girls High School Grimble Hall/Byron Block/Business Centre | ICB | No | Prior | January, 2026 | In progress |
| 73595-W-7 | Sandy Bay Secondary School Substitution | ICB | No | Prior | January 2026 | In progress |
| 73595-W-8 | Refurbishment and upgrading of the St. Clair Dacon Secondary School | ICB | No | Prior | February 2022 | Procurement completed |
| 73595-W-9 | Refurbishment and upgrading of the Thomas Saunders Secondary School | ICB | No | Prior | January 2026 | In progress |
| 73595-G-1 | Procurement of School Supplies (Furniture, ICT and TVET Equipment) | ICB | No | Prior | June 14, 2022 | Procurement completed for 3 completed schools |
|  | Procurement of School Supplies (Furniture, ICT and TVET Equipment) (New) | ICB |  |  |  | Following market review the procurement arrangements may be re-visited |
| 73595-G-2 | Office Equipment | LB (National) | No | Prior | January 15, 2021 | Procurement completed |

APPENDIX I

Page 3

| 73595-G3 | Project Vehicles | LB (National) | No | Prior | January 15, 2021 | Procurement completed |
| --- | --- | --- | --- | --- | --- | --- |
| 73595-G-5 | Procurement of universal screening/assessment tools for EIS: Goods (BASC-3, Behaviour assessment, 2 kits and 25 (packs of 25) record booklets; key Math-3, Achievement 3 kits and 25 sets of record booklets, TERA-4, 3 kits, and 25 sets of record booklets; TOWL-4, 3 kits and 25 sets of recod booklets; WICS-V, Weschler preschool and primary grade intelligence, 3 kits and 25 sets of record booklets, Achenbach Child Behviour Checklist) | ICB |  | Prior | March 2026 | These resources are to support the EIS programme. |

APPENDIX I

Page 4

| 73595-G-6 | Procurement of ECE Learning Materials Goods (Building blocks, puzzles, shape sorters, staking toys, picture books, story and sequencing cards, interactive books, Markers, play dough, Alphabet and number cards, phonics games, word and picture matching games, counting and sorting materials, number puzzles and games, measuring tools, emotion cards, sensory bins, textured toys, ball and sports equipment, balls) |  |  | ICB |  | Prior | March 2026 | To support the establishment of ECE classrooms in the following Primary schools: Chateaubelair ECC Troumaca ECC Park Hill ECC Colonarie ECC Owia ECC Edinboro ECC Greggs ECC Bequia Anglican ECC Fair Hall ECC South Rivers ECC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

APPENDIX I

Page 5

| 73595-G-7 | SEN Learning Resources: Goods (Assistive Devices - Screen readers and magnifiers, speech generating devices, adapted textbooks and reading materials, manipulatives, as tactile letters, charts, pictures, stress balls fidget spinners, weighted blankets, noise cancelling headphones, resistance bands) | ICB |  | Prior |  | To support the equipping of SEN classrooms in selected Primary School (Stephanie Browne Gov’t Barrouallie Anglican School Canouan Gov’t Bequia Anglican Primary Sandy Bay Gov’t) |
| --- | --- | --- | --- | --- | --- | --- |
| 73595-G-7 | Procurement of math learning resources | ICB |  | Prior | March 2026 | Listed in Appendix 10 |

APPENDIX I

Page 6

- Consulting Services

| Ref No. | Assignment (Description) | Selection Method | Review by Bank (Prior/Post) | Expected Proposal Submission Date | Comments |
| --- | --- | --- | --- | --- | --- |
| 73595-C-16 | Design and Supervision Services for the Rehabilitation and Construction of seven (7) project schools | QCBS | Prior | September 17, 2019 | Consultant has been engaged to undertake design and supervision services for the Infrastructure Works. |
| 73595-C-17 | Design and Supervision Services for Construction of Sandy Bay Secondary | QCBS | Prior | April 2023 | Consultant has been engaged to undertake design and supervision services for the Infrastructure Works. |
| 73595-C-18 | Design and Supervision Services for Construction of Thomas Saunders Secondary | QCBS | Prior | April 2023 | Consultant has been engaged to undertake design and supervision services for the Infrastructure Works |

APPENDIX I

Page 7

| 73595-C-19 | Financial audit | ICS | Prior | Dec, 2024 |  |
| --- | --- | --- | --- | --- | --- |
| 73595-C-20 | Project Engineer | ICS | Prior | November 30, 2024 | New Project Engineer is in place, contract was awarded November 29, 2024. |
| 73595-C-21 | Project Engineer (New) | ICS | Prior | Jan 2024 |  |
| 73595-C-22 | Project/Contract Assistant (New) | ICS | Post | Mar 2024 |  |
| 73595-C-23.1 | Institutional Strengthening Support Coordinator | ICS | Prior | Feb 2025 | Institutional Strengthening Coordinator is in place. |
| 73595-C-23.2 | Monitoring and Evaluation Officer | ICS | Prior | Feb 2025 |  |
| 73595-C-23.3 | Consultancy services to develop and implement Mathematics Improvement programme | DS | Prior | Feb 2025 |  |

APPENDIX I

Page 8

| 73595-C-23.4 | Mathematics Improvement Programme Coordinator | ICS | Prior | Feb 2025 | The Mathematics Improvement Coordinator is in place. |
| --- | --- | --- | --- | --- | --- |
| 73595-C-24 | Consultancy to update Education Act/Inclusive policy | QCBS | Prior | Jan 2025 |  |
| 73595-C-26 | Consultancy to develop and manage Public Awareness Strategy | CQS | Prior | Jan 2025 |  |
| 73595-C-27 | Consultancy to conduct accessibility Audit |  | Prior | Dec 2025 |  |
| 73595-C-28 | Consultancy to develop and implement in-service and pre-service inclusive education modules | DS | Prior | Jan 2026 |  |
| 73595-C-30 | Consultancy for the development and implementation of EIS. | DS | Prior | Dec 2026 |  |
| 73595-C-31 | Consultancy to develop Teacher Appraisal System | QCBS | Prior | Jan 2026 |  |
| 73595-C-32 | Consultancy to support the EMIS Policy and Masterplan | QCBS | Prior | July 2026 |  |

APPENDIX I

Page 9

- Procurement Capacity Building activities for the Implementing/Executing Agency

  - Project Launch Workshop: Completed in March 2021

  - The provision of online procurement e-learning by the CDB currently launched and available for enrolment monthly.

- Summary of Proposed Procurement Arrangement

| Project Components / Contracts |  | CDB ('000) |  |  |  |  | NBF ('000) |  | Total Cost ('000) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ICB |  | NCB | ICS | DS | QCBS | Counterpart | Co-Financing |  |
| Infrastructure Works |  |  |  |  |  |  |  |  |  |
| Goods |  |  |  |  |  |  |  |  |  |
| Procurement of School Supplies (Furniture, ICT and TVET Equipment) |  |  |  |  |  |  |  |  |  |
| Engineering and Construction- related Services |  |  |  |  |  |  |  |  |  |
| Project Management |  |  |  |  |  |  |  |  |  |
| Capacity Building: (Masters Degrees in Speech Therapy, Behaviour Therapy, Occupational Therapy, Dyslexia, Autism and Post Graduate Degree in Content & Pedagogy) |  |  |  |  |  |  |  |  |  |

APPENDIX I

Page 10

Goods, Works and Non-Consultancy Services

  - NCB - National Competitive Bidding

  - ICB - International Competitive Bidding

  - RCB - Regional Competitive Bidding

  - LB - Limited Bidding

  - DS - Direct Selection

  - FA - Force Account

  - CP - Commercial Practices

  - APA - Alternative Procurement Arrangements

  - NBF - Non-Bank Financed

  - Other

Consultancy Services:

- QCBS - Quality and Cost-Based Selection

- QBS - Quality-Based Selection

- FBS - Fixed Budget Selection

- LCS - Least-Cost Selection

- CQS - Consultants' Qualification Selection

- DS - Direct Selection

- CP - Commercial Practices

- APA - Alternative Procurement Arrangements

- ICS - Individual Consultants Selection

- NBF - Non-Bank Financed

- Other (as above)