## Sheet1
Project: Youth and Community Transformation Project
Loan Number: 60/SFR-BZE
Period covered: From April 2020 to December 2020
PROCUREMENT PLAN
Ref. No. 1 | Description of and Component of procurement contract | Procurement method 2 | Review by Bank | Source of financing and percentage |  | Prequalification 3 (Yes/No) | Estimated Dates |  | Status 4 (pending, in process, awarded, cancelled) | Comments | Additional Comments
|  |  |  | CDB % | Local / Other % |  | Publication of specific procurement notice | Signature of contract
1 | GOODS
E0 | Vehicle - 2 Passenger Vans and 1 4x4 Crewcab Pick-up Truck | Shopping | Prior | 100% | 0% | No | 2020-11-01 | 2020-12-01 | Awarded | ITQ for office supplies is presently being advertised with a deadline submission of Juy 4th, evaluation report to be submitted to IDB by 14th July, 2014 and contract signature July 21st, 2014 | Based on a local market survey, there were only limited suppliers who were able to supply vehicles from eligible countries; therefore no objection was provided to use the Shopping Procurement Method for procurement of these vehicles.
E4 | Funiture, Equipment and Learning Materials - Computers and Peripherals for the HUB | NCB | Prior | 100% | 0% | No | 2019-05-01 | 2020-06-01 | Awarded |  | Contract was signed June 12, 2020. This will be a direct payment from CDB so application was submitted to the Bank. There was an error in the advance payment guarantee and the Performance Bond was missing so supplier had to submit those. Pending documents were submitted to CDB August 4, 2020. Awaiting payment. Equipment has been supplied, delivered and installed and the final payment of the contract is in process.
E4 | Furniture, Equipment and Learning Supplies - Security Camera System | Shopping | Prior | 100% | 0% | No | 2020-07-01 | 2020-09-01 | Awarded |  | ITQ sent out to companies onn July 7th. Quotation deadline was July 22, 2020. Evaluation was conducted July 29th. Evaluation Report submitted to CDB August 4. Awaiting CDB's No Objection. Contract was signed in September 2020 and works were completed in November. Final payment is to be processed by December 31st.
E4 | Furniture, Equipment and Learning Supplies - Air Conditioning Units | Shopping | Post | 100% | 0% | No | 2020-03-01 | 2020-06-01 | Awarded |  | Contract was awarded to John Olivera Electrical and Construction and signed July 6, 2020. Direct payment from CDB, so the application has been submitted to CDB July 14th and we await payment. Works has taken much longer than anticipated. It should be finished before Dec 31st.
E4 | Furniture, Equipment and Learning Supplies - Music Equipment for Samuel Haynes Institute of Excellence | Shopping | Post | 100% | 0% | No | 2020-03-01 | 2020-07-01 | Awarded | Consultation with TWG for usage of software to be used in Primary schools. | Contract was awarded to Jacob Chehade and signed July 10, 2020. Direct Payment Application has been submitted to CDB July 22nd. We are awaiting payment. This contract has been completed and all payments made.
Subtotal
WORKS
P1 | Landscaping at the HUB (formerly LIRC) | NCB | Prior | 100% | 0% | No | TBD | TBD | Cancelled | In the process of getting rehabilitation Technical Specifications. Biding document to be submitted to IDB by July 14, 2014 | The ITQ has was approved by CDB May 15, 2020, and document has been shared with CEO Alpuche. Awaiting go ahead to invite bidders. Go ahead was not granted and there is now a new administration. This activity was not completed
Subtotal
CONSULTING SERVICES
T1 | Literacy and Numberacy - Facilitator the the HUB | SSS | Post | 100% | 0% | No | N/A | 2020-08-01 | 2020-09-01 | EOI is being published with deadline of June 14, 2014. Evaluation report to be submitted to IDB b 23rd, 2014 and contract signature by June 30th, 2014 | Facilitator needed to assist children at the HUB with homework, reading, etc. Facilitator, Damien Parchue was engaged in September and is working with children in small groups, to complete their assignments and offer support in areas that they are behind in. Payment is processed through the use of Purchase Orders.
T2 | Adaptive Life Skills - Life Skills Facilitator at the HUB | SSS | Post | 100% | 0% | No | N/A | 2020-08-01 | Awarded | Received IDB no-objection to Procurement package on March 3, 2014. EOI will be advertised by June 6th and deadline for submission is June 23rd. Evaluation report to be submitted by 30th June for possible contract award of 21 July, 2014 | Facilitators needed for the life skills sessions at the HUB, Same individual who was previously engaged will be retained. Will be engaged through the provision of a purchase order for services provided.
T3 | Community Support - Expressive Arts and Sports Facilitators at the HUB | SSS | Post | 100% | 0% | No | N/A | TBD | Cancelled | Awaiting IDB's no-objection to 'Technical and Price Proposal" Evaluation | Facilitators needed for the dance, jijitsu and sports programs. Persons who were previously engaged will be contacted to provide service. Similar to above, services will be provided through the provision of a purchase order. Due to the limited number of persons that can gather in a space, it was not possible to engage facilitators for this component at the HUB
C7 | Final Evaluation Consultancy | CQS | Prior | 100% | 0% | No | 2020-06-01 | 2020-09-01 | Awarded | Received IDB no-objection to Procurement package on March 3, 2014. EOI will be advertised by June 6th and deadline for submission is June 23rd. Evaluation report to be submitted by 30th June for possible contract award of 21 July, 2014 | Advertisement yielded 4 submissions. Evaluation will be done August 12, and report will be submitted to CDB thereafter. Contract was awarded to Dr. Abigail Mckay. Due to Covid she had some setbacks in gathering the data and needs additional time to produce the draft report. Dr. McKay has sent a formal request for extension and this has been sent to CDB and PSC for review. An extension is dependent on the project being granted an extension.
| End of Project Audit | CQS | Prior | 100% | 0% | No | 2020-06-01 | 2020-11-01 | Awarded | Received IDB no-objection to Procurement package on March 3, 2014. EOI will be advertised by June 6th and deadline for submission is June 23rd. Evaluation report to be submitted by 30th June for possible contract award of 21 July, 2014 | Contract was awarded to Bakertilly Auditing Firm. They too experienced some setbacks and have not submitted draft report. Their first payment also took a long time to be processed and a value date of December 9 was confirmed. It is expected the draft report will be submitted before December 31st.
SubTotal
Grand Total
Updated December 16, 2020